## Sheet1
Task Level 1 |  | Task Level 2 |  | Task | Task Level 3 |  | Task Number | Jacob | Malika | Nicholas | Erich | Dawson | Catherine | Abigail | Total Effort | Start | Finish | Duration | Jacob/WK | Malika/WK | Nicholas/WK | Erich/WK | Hannah/WK | Catherine/WK | Complete | Comments
Gather Geospatial Data | 1 | Utility Infrastructure Mapping | 1 | 1.1.1 - Digitize Target Substations | Digitize Target Substations | 1 | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 32 | 2019-04-16 | 2019-04-29 | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 100
Gather Geospatial Data | 1 | Utility Infrastructure Mapping | 1 | 1.1.2 - Digitize 3PH Network | Digitize 3PH Network | 2 | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 328 | 2019-04-16 | 2019-08-30 | 99 | 0 | 0 | 0 | 0 | 0 | 16.5657 | 50 | based on the amount of 3 phase Catherine/(Hannah) have finished to date, 5/22. Four counties complete which took 160 hours by Catherines estimates. With about 5 more counties that have what look to be a lot of open flat farm land are what the hours estimated are based on.
Gather Geospatial Data | 1 | Utility Infrastructure Mapping | 1 | 1.1.3 - Hosting Capacity Analysis | Hosting Capacity Analysis | 3 | 1.1.3 | 16 | 0 | 0 | 0 |  | 16 | 0 | 32 | 2019-06-10 | 2019-08-30 | 60 | 1.3333 | 0 | 0 | 0 | 0 | 1.3333 | 0 | based on 30 capacity screens in Ameran. Depends on number of substations & number of pre-applications (information from Malika + Catherine)
Gather Geospatial Data | 1 | Physical Constraints Analysis | 2 | 1.2.1 - Identify Geospatial Constraints | Identify Geospatial Constraints | 1 | 1.2.1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2019-03-22 | 2019-08-30 | 116 | 0.68966 | 0 | 0 | 0 | 0 | 0 | 0 | Westwood constraints matrix needed
Gather Geospatial Data | 1 | Physical Constraints Analysis | 2 | 1.2.2 - Collect, organize, and clean geospatial data | Collect, organize, and clean geospatial data | 2 | 1.2.2 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 2019-03-02 | 2019-08-30 | 130 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 80 | Westwood constraints matrix needed
Prepare suitability maps | 2 | Update Suitability Analysis Model | 1 | 2.1.1 - Update Macro Level Geospatial Constraints Model | Update Macro Level Geospatial Constraints Model | 1 | 2.1.1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2019-06-10 | 2019-08-30 | 60 | 1.3333 | 0 | 0 | 0 | 0 | 0 | 0
Prepare suitability maps | 2 | Update Suitability Analysis Model | 1 | 2.1.2 - Update Utility Infrastructure Model | Update Utility Infrastructure Model | 2 | 2.1.2 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | discussion with Erich needed
Prepare suitability maps | 2 | Create Suitability Maps | 2 | 2.2.1 - Create & Clean Addressing Database | Create & Clean Addressing Database | 1 | 2.2.1 | 0 | 0 | 0 | 8 | 12 | 12 | 0 | 32 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.66667 | 1 | 1 | 0 | discussion with Erich & Nicholas(?) needed
Prepare suitability maps | 2 | Create Suitability Maps | 2 | 2.2.2 - Aggregate sites by owner | Aggregate sites by owner | 2 | 2.2.2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | Unsure
Prepare suitability maps | 2 | Create Suitability Maps | 2 | 2.2.3 - Create Site Maps by Owner | Create Site Maps by Owner | 3 | 2.2.3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | Scripts Erich runs
Prepare suitability maps | 2 | Create Suitability Maps | 2 | 2.2.4 - Manually Review and Edit Ownermaps | Manually Review and Edit Ownermaps | 4 | 2.2.4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 2019-06-10 | 2019-08-30 | 60 | 0.66667 | 0.66667 | 0 | 0 | 0 | 0 | 0
Landowner Outreach | 3 | Letter Outreach | 1 | 3.1.1 - Update letter outreach materials | Update letter outreach materials | 1 | 3.1.1 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 6 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0.33333 | 0 | 0.16667 | 0 | 0 | 0 | Unsure
Landowner Outreach | 3 | Letter Outreach | 1 | 3.1.2 - Develop Mail Merge database | Develop Mail Merge database | 2 | 3.1.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.083333 | 0 | 0 | 0 | Unsure
Landowner Outreach | 3 | Letter Outreach | 1 | 3.1.3 - Run Mail Merge | Run Mail Merge | 3 | 3.1.3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.083333 | 0 | 0 | 0 | weary about this
Landowner Outreach | 3 | Letter Outreach | 1 | 3.1.4 - Print letters | Print letters | 4 | 3.1.4 | 8 | 8 | 8 | 0 | 8 | 8 | 0 | 40 | 2019-06-10 | 2019-08-30 | 60 | 0.66667 | 0.66667 | 0.66667 | 0 | 0.66667 | 0.66667 | 0 | depending on letter amount
Landowner Outreach | 3 | Letter Outreach | 1 | 3.1.5 - Create PDF of each letter | Create PDF of each letter | 5 | 3.1.5 | 8 | 8 | 8 | 0 | 8 | 8 | 0 | 40 | 2019-06-10 | 2019-08-30 | 60 | 0.66667 | 0.66667 | 0.66667 | 0 | 0.66667 | 0.66667 | 0 | depending on letter amount
Landowner Outreach | 3 | Postcard Outreach | 2 | 3.2.1 - Update postcard outreach materials | Update postcard outreach materials | 1 | 3.2.1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | I assume this is something Erich does
Landowner Outreach | 3 | Postcard Outreach | 2 | 3.2.2 - Update mail merge database removing contacted | Update mail merge database removing contacted | 2 | 3.2.2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | Unsure
Landowner Outreach | 3 | Postcard Outreach | 2 | 3.2.3 - Print postcards | Print postcards | 3 | 3.2.3 | 8 | 8 | 8 | 0 | 8 | 8 | 0 | 40 | 2019-06-10 | 2019-08-30 | 60 | 0.66667 | 0.66667 | 0.66667 | 0 | 0.66667 | 0.66667 | 0
Hand off materials | 4 | Post to SharePoint | 1 | 4.1.1 - Upload Letter PDFs | Upload Letter PDFs | 1 | 4.1.1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 2019-06-10 | 2019-08-30 | 60 | 0.16667 | 0 | 0.16667 | 0 | 0 | 0 | 0 | Unsure
Hand off materials | 4 | Post to SharePoint | 1 | 4.1.2 - Upload KMZs | Upload KMZs | 2 | 4.1.2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 2019-06-10 | 2019-08-30 | 60 | 0.16667 | 0 | 0.16667 | 0 | 0 | 0 | 0 | Unsure
Hand off materials | 4 | Update Zoho | 2 | 4.2.1 - Create Zoho input key | Create Zoho input key | 1 | 4.2.1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | Unsure
Hand off materials | 4 | Update Zoho | 2 | 4.2.2 - Upload Zoho input key | Upload Zoho input key | 2 | 4.2.2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2019-06-10 | 2019-08-30 | 60 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | Unsure
Hand off materials | 4 | Baselayers Support | 3 | 4.3.1 - Create Baselayers | Create Baselayers | 1 | 4.3.1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2019-04-24 | 2019-08-30 | 93 | 0.43011 | 0 | 0 | 0 | 0 | 0 | 25
Hand off materials | 4 | Baselayers Support | 3 | 4.3.2 - Create automated Baselayers Update Script | Create automated Baselayers Update Script | 2 | 4.3.2 | 8 | 0 | 0 | 4 | 0 | 0 | 0 | 12 | 2019-04-24 | 2019-08-30 | 93 | 0.43011 | 0 | 0 | 0.21505 | 0 | 0 | 25
Hand off materials | 4 | Baselayers Support | 3 | 4.3.3 - Maintain Baselayers | Maintain Baselayers | 3 | 4.3.3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2019-06-10 | 2019-08-30 | 60 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Duration = NETWORKDAYS([Start],[Finish])